## Sheet1
Bellabeat's Fitbit Analysis: Integrating Data and Project Management |  |  |  |  | Week1 |  |  |  |  | Week2 | [8 empty] | Week3
Tasks | Status | Start Date | End Date | Days | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07
Phase 1: Assess the Need | Complete | 2023-06-19 | 2023-06-22 | 4
Clearly identify the problem and solution | Complete | 2023-06-19 | 2023-06-19 | 1
Define Project Scope and Objectives | Complete | 2023-06-19 | 2023-06-19 | 1
Identify Key Stakeholders | Complete | 2023-06-20 | 2023-06-20 | 1
Conduct Stakeholder Needs | Complete | 2023-06-21 | 2023-06-21 | 1
Create Project Charter | Complete | 2023-06-22 | 2023-06-22 | 1
Phase 2: Data Governance Protocols | Complete | 2023-06-26 | 2023-06-30 | 5
Define data source | Complete | 2023-06-26 | 2023-06-26 | 1
Establish Data Gornance and Privacy Protocols | Complete | 2023-06-26 | 2023-06-26 | 1
Phase 3: Data Discovery and Preprocessing | In Progress | 2023-06-23 | 2023-07-03 | 7
Perform data cleaning | In Progress | 2023-06-26 | 2023-06-26 | 1
Perform data transformation and standardasation | In Progress | 2023-06-27 | 2023-06-27 | 1
Phase 4 Title: Data Analysis and Insight Generation | Needs Update | 2023-06-29 | 2023-07-04 | 4
Perform Exploratory Data Analysis (EDA) | Needs Update | 2023-06-29 | 2023-06-29 | 1
Create Chart and Visualization with R | Needs Update | 2023-06-30 | 2023-06-30 | 1
Phase 5: Recommendation Development | Complete | 2023-07-03 | 2023-07-05 | 3
Establish Findings Compilation | Complete | 2023-07-03 | 2023-07-03 | 1
Determine Objective Alignment | Needs Update | 2023-07-04 | 2023-07-04 | 1
Assess Risk Assessment | Complete | 2023-07-04 | 2023-07-04 | 1
Phase 6: Data Insights Delivery and Stakeholder Decision Meeting | In Progress | 2023-07-04 | 2023-07-04 | 1
Presentation Preparation | Needs Update | 2023-07-05 | 2023-07-05 | 1
Stakeholder engagement | Not Started | 2023-07-05 | 2023-07-05 | 1
Presentation Delivery and Feedback gathering | In Progress | 2023-07-07 | 2023-07-07 | 1
Decision Making | On Hold | 2023-07-07 | 2023-07-07 | 1